## Sheet1 (hidden)
Data processing, reviewing rejections and communicating to the stakeholders - SLA - Daily data that
is received is processed within 2 hours, any issues with data are reported within 1 hour of the data
processing
2. Support management - categorising tickets, assigning tickets to the developers and communicating
to the end-users. SLA - support available 9-5:30 UK hours via phone and email
3. Bugs fixing: Any issues reported by the client on the live modules
4. Assessing client requests, estimating efforts and flagging changes to Haymarket
5. If there is spare time, automating and optimising the processes/ systems
6. Users Access management - SLA - best endeavour to resolve any issues within 1 day
7. Infrastructure management on an ongoing basis while TMotions are hosting.
| Allocated | Actual
Project Management | 12 | 12
Data Processing | 21 | 21
Support Management | 21 | 21
Bug Fixing | 10 | 10
Optimization and Tech Debt | 15 | 15
Infra Management | 4 | 4
CRs | 4 | 12
New Projects discussion |  | 4
Total | 87 | 99
Allocated |  | 87
Extra |  | 12
Extra CRs |  | 8
Extra new project disc |  | 4

## Actual Report
MONTHLY SLA REPORT - PERFORMANCE PORTAL ¦ JULY 2021
This report provides monthly snapshot of contractual SLAs for Performance Portal
Data Processing Files |  |  |  | Support Management | [6 empty] | Change Management | [5 empty] | Process Optimisation Initiatives
0 |  |  |  | 0 | [6 empty] | 0 | [5 empty] | 0
0% |  | 0% |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
SLA deviation in error reporting |  | SLA deviation in file processing |  | # of User Access Tickets |  |  | # of Non-User Access Tickets |  |  |  | # of CRs Analysed |  | # of CRs approved |  |  |  | # of tasks completed
DATA PROCESSING FEEDS |  |  |  |  | ⃝
Adhoc feeds Summary
Commentary
SLA Impact Summary
SUPPORT MANAGEMENT
|  |  | AUDI |  | SEAT |  |  | SKODA |  | VWCV |  | VWPC |  | TOTAL
Total support tickets received |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
# of new tickets |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
# of open tickets at eom |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
Closed |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
Resolved (waiting for clousre) |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
Pending |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
User access |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
SLA deviation in User tickets (SLA: 24 hrs) |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
CHANGE MANAGEMENT
|  |  | AUDI |  |  | SEAT |  |  | SKODA |  |  | VWCV |  |  | VWPC |  |  | TOTAL
# of CRs Analysed |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Total effort estimated (person-days) |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
# of CRs approved |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Total effort estimate approved (person-days) |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
PROCESS OPTIMISATION INITIATIVE
S.No. | Brand | Module | Issue | [5 empty] | Solution |  |  |  | Result |  |  | Status

## basegraphdata
Plan vs Act
AUDI |  |  |  | SEAT |  |  |  | SKODA |  |  | VWCV |  |  |  | VWPC
FREQ. | PLANNED | ACTUAL |  | FREQ. | PLANNED | ACTUAL |  | FREQ. | PLANNED | ACTUAL | FREQ. | PLANNED | ACTUAL |  | FREQ. | PLANNED | ACTUAL
YEARLY | 0 | 0 |  | YEARLY | 0 | 0 |  | YEARLY | 0 | 0 | YEARLY | 0 | 0 |  | YEARLY | 0 | 0
MONTHLY | 0 | 0 |  | MONTHLY | 0 | 0 |  | MONTHLY | 0 | 0 | MONTHLY | 0 | 0 |  | MONTHLY | 0 | 0
WEEKLY | 0 | 0 |  | WEEKLY | 0 | 0 |  | WEEKLY | 0 | 0 | WEEKLY | 0 | 0 |  | WEEKLY | 0 | 0
DAILY | 42 | 9 |  | DAILY | 0 | 0 |  | DAILY | 0 | 0 | DAILY | 0 | 0 |  | DAILY | 0 | 0
Adhoc feeds Summary
AUDI |  |  |  | SEAT |  |  |  | SKODA |  |  | VWCV |  |  |  | VWPC
FREQ. | RECEIVED | PROCESSED |  | FREQ. | RECEIVED | PROCESSED |  | FREQ. | RECEIVED | PROCESSED | FREQ. | RECEIVED | PROCESSED |  | FREQ. | RECEIVED | PROCESSED
YEARLY | 50 | 10 |  | YEARLY | 0 | 0 |  | YEARLY | 0 | 0 | YEARLY | 0 | 0 |  | YEARLY | 0 | 0
MONTHLY | 0 | 0 |  | MONTHLY | 0 | 0 |  | MONTHLY | 0 | 0 | MONTHLY | 0 | 0 |  | MONTHLY | 0 | 0
WEEKLY | 0 | 0 |  | WEEKLY | 0 | 0 |  | WEEKLY | 0 | 0 | WEEKLY | 0 | 0 |  | WEEKLY | 0 | 0
DAILY | 42 | 8 |  | DAILY | 0 | 0 |  | DAILY | 0 | 0 | DAILY | 0 | 0 |  | DAILY | 0 | 0
SLA Impact Summary
AUDI | [5 empty] | SEAT |  |  |  |  | SKODA | [5 empty] | VWCV |  |  |  |  | VWPC
Data Feeds | DAILY | WEEKLY | MONTHLY | YEARLY |  | Data Feeds | DAILY | WEEKLY | MONTHLY | YEARLY | Data Feeds | DAILY | WEEKLY | MONTHLY | YEARLY |  | Data Feeds | DAILY | WEEKLY | MONTHLY | YEARLY | Data Feeds | DAILY | WEEKLY | MONTHLY | YEARLY
Error reporting SLA deviation | 0 | 0 | 0 | 0 |  | Error reporting SLA deviation | 0 | 0 | 0 | 0 | Error reporting SLA deviation | 0 | 0 | 0 | 0 |  | Error reporting SLA deviation | 0 | 0 | 0 | 0 | Error reporting SLA deviation | 0 | 0 | 0 | 0
File processing SLA deviation | 0 | 0 | 0 | 0 |  | File processing SLA deviation | 0 | 0 | 0 | 0 | File processing SLA deviation | 0 | 0 | 0 | 0 |  | File processing SLA deviation | 0 | 0 | 0 | 0 | File processing SLA deviation | 0 | 0 | 0 | 0
Total files received | 0 | 0 | 0 | 0 |  | Total files received | 0 | 0 | 0 | 0 | Total files received | 0 | 0 | 0 | 0 |  | Total files received | 0 | 0 | 0 | 0 | Total files received | 0 | 0 | 0 | 0
SUPPORT MANAGEMENT
Month | User Access tickets | Non user access tickets | Month | User Access Tickets | Non User Access tickets | Total tickets
| 10% | 90% | 0 | 0 | 0 | 0

## mockupv1.1 (hidden)
MONTHLY SUPPORT SLA REPORT - PERFORMANCE PORTAL ¦ MON YYYY
This report provides monthly snapshot of contratual SLAs for Performance Portal
26 |  |  | 10 | [5 empty] | 10 | [5 empty] | 5 | [5 empty] | 5
# of Data Processing Feeds |  |  | # of Support Management Tickets | [5 empty] | # of Change Management Tickets | [5 empty] | # of User Access Tickets | [5 empty] | # of Process Optimization Initiatives
2% | 0% |  | 7 |  | 10 |  |  |  | 5 |  | 4 |  |  |  | 0% | [5 empty] | 2%
% error reporting deviation | % file processing deviation |  | # of Bug fixes |  | # of Resolved Tickets |  |  |  | # of CRs Analyzed |  | # of CRs approved |  |  |  | % SLA deviation | [5 empty] | MoM Growth
DATA PROCESSING FEEDS
KPIs |  | AUDI |  |  |  | SEAT |  |  |  | SKODA | [5 empty] | VWCV | [5 empty] | VWPC |  | VWG
|  | DAILY |  | WEEKLY |  | WEEKLY |  | YEARLY |  | DAILY |  | WEEKLY |  | YEARLY |  | WEEKLY |  | MONTHLY |  | YEARLY |  | YEARLY |  | TOTAL
|  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL
# of files processed |  | 6 | 6 | 3 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 22
SLA Deviation- Errort Reporting (SLA: 1hr) |  | N/A | 1 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 1 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 1 | N/A | 0 | 3
SLA Deviation- File Processing (SLA: 2hrs) |  | N/A | 0 | N/A | 0 | N/A | 1 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 1 | N/A | 0 | N/A | 1 | N/A | 0 | N/A | 0 | 3
SUPPORT MANAGEMENT
|  | AUDI |  |  |  | SEAT |  |  |  | SKODA |  |  |  | VWCV |  |  |  | VWPC |  |  |  | TOTAL
Total support tickets received |  | 10 |  |  |  | 3 |  |  |  | 7 |  |  |  | 4 |  |  |  | 1 |  |  |  | 25
Bug Fixes |  | 4 |  |  |  | 1 |  |  |  | 4 |  |  |  | 2 |  |  |  | 1 |  |  |  | 12
XYZ category |  | 4 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 0 |  |  |  | 7
ABC category |  | 2 |  |  |  | 1 |  |  |  | 2 |  |  |  | 1 |  |  |  | 0 |  |  |  | 6
Resolved in the month |  | 8 |  |  |  | 3 |  |  |  | 6 |  |  |  | 4 |  |  |  | 1 |  |  |  | 22
Total support tickets deferred/Unassigned bugs |  | 2 |  |  |  | 0 |  |  |  | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 3
CHANGE MANAGEMENT
|  | AUDI |  |  |  | SEAT |  |  |  | SKODA |  |  |  | VWCV |  |  |  | VWPC |  |  |  | TOTAL
# of CRs Analyzed |  | 3 |  |  |  | 2 |  |  |  | 0 |  |  |  | 1 |  |  |  | 0 |  |  |  | 6
Total effort estimated (mandays) |  | 15 |  |  |  | 10 |  |  |  | 0 |  |  |  | 7 |  |  |  | 0 |  |  |  | 32
# of CRs approved |  | 2 |  |  |  | 2 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 4
Total effort estimate approved (mandays) |  | 10 |  |  |  | 10 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 20
USER ACCESS MANAGEMENT
|  | AUDI |  |  |  | SEAT |  |  |  | SKODA |  |  |  | VWCV |  |  |  | VWPC |  |  |  | TOTAL
# of user access tickets received |  | 3 |  |  |  | 2 |  |  |  | 0 |  |  |  | 1 |  |  |  | 0 |  |  |  | 6
# of user access tickets resolved |  | 3 |  |  |  | 2 |  |  |  | 0 |  |  |  | 1 |  |  |  | 0 |  |  |  | 6
# of tickets with SLA deviation (SLA: 24 hrs) |  | 0 |  |  |  | 1 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 1
PROCESS OPTIMIZATION INITITATIVES
S.No. | Description | [10 empty] | Status
1 | xyz | [10 empty] | Completed
2 | abc | [10 empty] | Completed
3 | pqr | [10 empty] | In Progress
4 | def | [10 empty] | In Progress
5 | lmn | [10 empty] | Deferred
TMOTIONS highly confidential: For Internal Use Only

## mockupv1.2 (hidden)
MONTHLY SLA REPORT - PERFORMANCE PORTAL ¦ MON YYYY
This report provides monthly snapshot of contratual SLAs for Performance Portal
26 |  |  | 10 |  |  | 10 |  |  |  |  | 5 |  | 5
# of Data Processing Feeds |  |  | # of Support Management Tickets |  |  | # of Change Management Tickets |  |  |  |  | # of User Access Tickets |  | # of Process Optimization Initiatives
2% | 0% |  | 7 | 10 |  | 5 |  | 4 |  |  | 0% |  | 2%
% error reporting deviation | % file processing deviation |  | # of Bug fixes | # of Resolved Tickets |  | # of CRs Analyzed |  | # of CRs approved |  |  | % SLA deviation |  | MoM Growth
DATA PROCESSING FEEDS
SUPPORT MANAGEMENT
|  | AUDI |  |  | SEAT |  | SKODA |  |  | VWCV |  | VWPC |  | TOTAL
Total support tickets received |  | 10 |  |  | 3 |  | 7 |  |  | 4 |  | 1 |  | 25
Bug Fixes |  | 4 |  |  | 1 |  | 4 |  |  | 2 |  | 1 |  | 12
XYZ category |  | 4 |  |  | 1 |  | 1 |  |  | 1 |  | 0 |  | 7
ABC category |  | 2 |  |  | 1 |  | 2 |  |  | 1 |  | 0 |  | 6
Resolved in the month |  | 8 |  |  | 3 |  | 6 |  |  | 4 |  | 1 |  | 22
Total support tickets deferred/Unassigned bugs |  | 2 |  |  | 0 |  | 1 |  |  | 0 |  | 0 |  | 3
CHANGE MANAGEMENT
|  | AUDI |  |  | SEAT |  | SKODA |  |  | VWCV |  | VWPC |  | TOTAL
# of CRs Analyzed |  | 3 |  |  | 2 |  | 0 |  |  | 1 |  | 0 |  | 6
Total effort estimated (mandays) |  | 15 |  |  | 10 |  | 0 |  |  | 7 |  | 0 |  | 32
# of CRs approved |  | 2 |  |  | 2 |  | 0 |  |  | 0 |  | 0 |  | 4
Total effort estimate approved (mandays) |  | 10 |  |  | 10 |  | 0 |  |  | 0 |  | 0 |  | 20
USER ACCESS MANAGEMENT
|  | AUDI |  |  | SEAT |  | SKODA |  |  | VWCV |  | VWPC |  | TOTAL
# of user access tickets received |  | 3 |  |  | 2 |  | 0 |  |  | 1 |  | 0 |  | 6
# of user access tickets resolved |  | 3 |  |  | 2 |  | 0 |  |  | 1 |  | 0 |  | 6
# of tickets with SLA deviation (SLA: 24 hrs) |  | 0 |  |  | 1 |  | 0 |  |  | 0 |  | 0 |  | 1
PROCESS OPTIMIZATION INITITATIVES
S.No. | Description | [7 empty] | Status
1 | xyz | [7 empty] | Completed
2 | abc | [7 empty] | Completed
3 | pqr | [7 empty] | In Progress
4 | def | [7 empty] | In Progress
5 | lmn | [7 empty] | Deferred
TMOTIONS highly confidential: For Internal Use Only

## Sheet2 (hidden)
|  | Daily | weekly | Monthly | Yearly | Total Actual | Expected
Audi | Aftersales bonus | 21/21 | 18 15/16 +3extra | 0 | 0 | 39 | 36
| Approved used | 21/21 | 4/5 |  |  | 25 | 26
| Fleet | 09/21 | N/A |  |  | 09 | 21
|  | 51 | 22 |  |  | 73
Seat | Roadside & cambelt | N/A | 15/12 |  |  | 15 | 12
| Sales forecasting |  | 8/8 |  |  | 8 | 8
|  |  | 23 |  |  | 23
Skoda | Fleet | 126/62 |  |  |  | 126 | 62
| Sales forecasting |  | 16/16 |  |  | 16 | 16
|  | 126 | 16 |  |  | 142
VWCV | Aftersales forecasting |  |  | 1/1 |  | 1 | 1
| Aftersales contracting |  |  | 1/1 |  | 1 | 1
|  |  |  | 2 |  | 2
[6 empty] | 240 | 183